## Sheet1
Task | Sub Tasks | Est. Time (hours) | Assigned to: | Status
Map:
| Create Prehabs | 1h | Juan | Pending
| Dummy Map | 1h | Juan | Pending
| Procedural | 20h | Juan | Pending
UI
| Health | 0.5h | Run Ming | Pending
| Mini Map | 10h | Run Ming | Pending
| Ammo | 0.5h | Run Ming | Pending
| Damage | 0.5h | Run Ming | Pending
| Time | 0.5h | Run Ming | Pending
VFX
| Particals | 1h | Run Ming | Pending
| Lighting | 1h | Run Ming | Pending
| Materials | 1h | Run Ming | Pending
Ai
| Searching | 5h | Kim | Pending
| Pathfinding | 5h | Kim | Pending
| States | 1h | Kim | Pending
| Combat | 2h | Kim | Pending
Gravity Controller
| gravity | 10h | Shaun | Pending
Combate System
| Weapons | 1h x weapon | Dong | Pending
| Damage System | 0.5h | Dong | Pending
| Range | 0.5h | Dong | Pending
| Power ups | 0.5h | Dong | Pending
| rocket launcher | 2h | Dong | Pending