## Sheet1
Task | Sub Tasks | Est. Time | Assigned to | Status | Priority
Map:
| Create Prehabs | 1h | Juan | Done | High
| Dummy Map | 1h | Juan | Done | High
| Procedural | 20h | Juan | In Progress | Medium
UI:
| Health | 0.5h | Run Ming | Done | low
| Mini Map | 10h | Run Ming | Done | high
| Ammo | 0.5h | Run Ming | Done | low
| Damage | 0.5h | Run Ming | Done | low
| Time | 0.5h | Run Ming | Done | low
VFX:
| Particles | 0.5h | Run Ming | Done | Medium
| .Gun Fire | 10m | Run Ming | Done | Medium
| .Smoke | 10m | Run Ming | Done | Medium
| .Explosions | 10m | Run Ming | Done | Medium
| .Lazer flare | 10m | Run Ming | Done | Medium
| .Blood | 10m | Run Ming | Done | Medium
| Lighting | 1h | Run Ming | Done | Medium
| Materials | 1h | Run Ming | Done | Medium
Ai:
| Searching | 5h | Kim | Done | high
| Pathfinding | 5h | Kim | Done | high
| States | 1h | Kim | Done | Medium
| Combat | 2h | Kim | In Progress | Medium
Gravity Controller:
| Player Controller | 2h | Shaun | Done | high
| Player Health | 0.5h | Shaun | Done | medium
| gravity | 2h | Shaun | Done | high
Combate System:
| Weapons | 1h x weapon | Dong | Done | high
| .shotgun | 0.5h | Dong | Done | Medium
| .rifle | 0.5h | Dong | Done | Medium
| .rocket launcher | 2h | Dong | Done | high
| .Lazer gun | 0.5h | Dong | Done | high
| Damage System | 0.5h | Dong | Done | Medium
| Range | 0.5h | Dong | Done | Medium
| Power ups | 0.5h | Dong | Done | low
| health | 0.5h | Dong | Done | low